## Sheet1
GRAP 104 Reference Group plan and performance |  | Grey shaded | No outputs for performance target | [8 empty] | Grey shaded | No outputs for performance target | [10 empty] | Grey shaded | No outputs for performance target
|  | Green text | Amendments to workplan agreed by RG | [8 empty] | Green text | Amendments to workplan agreed by RG | [10 empty] | Green text | Amendments to workplan agreed by RG
|  | Red text | Performance target not met | [8 empty] | Red text | Performance target not met | [10 empty] | Red text | Performance target not met
Outputs | Plan 2023/24 |  |  |  |  | Actual 2023/24 |  |  |  |  | Plan 2024/25 |  |  |  |  | Actual 2024/25 |  |  |  |  | Plan 2025/26 |  |  |  |  | Actual 2025/26
| Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q2 | Q3 | Q4 | Total | Q1 | Q3 (meeting 1) | Q3 (meeting 2) | Q4 | Total | Q1 | Q3 (meeting 1) | Q3 (meeting 2) | Q4 | Total | Q1 | Q3 (meeting 1) | Q3 (meeting 2) | Q4 | Total | Q1 | Q3 (meeting 1) | Q3 (meeting 2) | Q4 | Total
VAT - Review proposed actions | Fact Sheet done in March '23 |  |  |  |  | Fact Sheet done in March '23
Loan commitments and concessionary loans - Overview of requirements | X |  |  |  |  | June meeting held in July | X
Discussion of investments to be covered
Loan commitments and concessionary loans - Discussion of issues by preparers + identify proposed actions - No specific deliverable
Inter-entity loans - Overview of requirements |  | X |  |  |  |  | X
Investments - Overview of requirements |  | Postpone to bring forward disclosures |  | X |  |  | Postpone to bring forward disclosures |  | March meeting to be held in April | [6 empty] | X March meeting held in April
Disclosure - Overview of requirements |  | X Only planned for 2025/26 |  |  |  |  | X
Loan commitments and concessionary loans - Review proposed actions |  |  | X |  |  |  |  | X Fact sheet and flow chart
Disclosure - Review of proposed actions |  |  | X Only planned for 2025/26 |  |  |  |  | X 2x Fact sheets
Inter-entity loans - Discussion of issues by preparers + identify proposed actions - No specific deliverable
Investments - Discussion of issues by preparers + identify proposed actions - No specific deliverable [Postponed]
Inter-entity loans - Review proposed actions |  |  |  | No actions identified |  |  |  |  | N/A - none identified
Investments - Review proposed actions |  |  |  | Postpone to bring forward disclosures |  |  |  |  | Postpone to bring forward disclosures
Revolving credit facilities - Overview of requirements and discuss prevalence – decide next steps |  |  |  | X |  |  |  |  | March meeting to be held in April | [6 empty] | X March meeting held in April
Disclosure - Discussion of issues by preparers + identify proposed actions - No specific deliverable
Financial guarantee contracts - overview of requirements | [10 empty] | X |  |  |  |  | X
Revolving credit facilities - overview of requirements from perspective of holder | [10 empty] | X Agreed at April meeting to add |  |  |  |  | X
Investments - Discussion of issues by preparers + identify proposed actions - No specific deliverable
Investments - Review proposed actions | [11 empty] | X (2 fact sheets) |  |  |  |  | X Review of 2 Fact Sheets
Financial guarantee contracts - Discussion of issues by preparers + identify proposed actions - No specific deliverable
Presentation to recap topics and consider identified issues - Unallocated deposits, consumer deposits, debtors with interest-free extended payment terms, employee benefits, staff bursaries, unspent conditional grants | [11 empty] | X Agreed at December 2023 meeting |  |  |  |  | X Presentation delivered
Financial guarantee contracts - Review of proposed actions | [12 empty] | X Fact Sheet |  |  |  |  | X Fact Sheet
Concessionary loans received - Overview of requirements | [12 empty] | X |  |  |  |  | X presentation
GRAP 104 placemat | [17 empty] | X Placemat
Concessionary loans - Discussion of issues by preparers + identify proposed actions
Presentation of financial instruments - Discussion of issues by preparers + identify proposed actions
IASB® Amendments to the Classification and Measurement of Financial Instruments: amendments related to assessing contractual cash flow characteristics of financial assets, including those with ESG-linked features - Overview of requirements | [13 empty] | X Presentation |  |  |  |  | X Presentation
Concessionary loans payable - Review of guidance | [20 empty] | X Fact Sheet |  |  |  |  | X Fact Sheet
Liabilities (distinction between liabilities, equity and revenue) - Overview of requirements | [20 empty] | X Presentation |  |  |  |  | X Presentation
Discuss what potential issues exist (discounting + embedded derivatives), and identify next steps - discussion of potential issues
Issues identified by members: practical considerations for impairment of contractual and statutory receivables: Discussion of issues
Liabilities (distinction between liabilities, equity and revenue) - Review of proposed actions | [21 empty] | X
Recap of changes and communication - Review of guidance issued and identify potential issues | [22 empty] | X
Education sessions | [22 empty] | X | X
CALCULATION FOR PERFORMANCE INFORMATION
#DELIVERED | [5 empty] | 0 | 3 | 2 | 0 | 5 | [5 empty] | 4 | 3 | 3 | 1 | 11 | [5 empty] | 2 | 0 | 0 | 0 | 2
#TO BE DELIVERED | 1 | 2 | 2 | 2 | 7 | 1 | 2 | 2 | 2 | 7 | 2 | 3 | 2 | 1 | 8 | 2 | 3 | 2 | 1 | 8 | 2 | 1 | 2 | 1 | 6 | 2 | 1 | 2 | 1 | 6
% DELIVERED | [5 empty] | 0% | 150% | 100% | 0% | 71.43% | [5 empty] | 200% | 100% | 150% | 100% | 137.5% | [5 empty] | 100% | 0% | 0% | 0% | 33.33%
[16 empty] | Quarter 3: 6/5 delivered = |  | 120% | [7 empty] | Quarter 3:
Note on M6: Elizna van der Westhuizen: Meeting in October
Note on N6: Elizna van der Westhuizen: Meeting in December
Note on W6: Elizna van der Westhuizen: Meeting in October
Note on I7: Elizna van der Westhuizen: Jeanine, in this quarter the group gave input to the OAG's contractual receivables guideline, which was the other outcome agreed for VAT. I haven't counted it since it wasn't anything we developed or published. Do you agree?