## Monitoring convergence IPSAS
MONITORING CONVERGENCE WITH THE IPSASB | [5 empty] | Project milestones
PROJECT |  | SECRETARIAT |  | CURRENT STATUS AND LOCAL IMPACT | [5 empty] | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
2023/24
QUARTER 1
[6 empty] | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 |  | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 |  | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 |  |  | QUARTER 2 | QUARTER 3 | QUARTER 4
MONITORING
| Public Sector Combinations |  | A Botha |  | IPSAS project concluded. Amendments to GRAP 105 - GRAP 107 finalised. Effective date is 1 April 2027.
| Social Benefits |  | E van der Westhuizen |  | IPSAS 42 finalised. Monitor whether IPSASB will conduct a post-implementation review. Board to approve final Standard March 2026.
| Public Sector Financial Instruments |  | J Poggiolini |  | IPSAS 41 finalised. Amendments to GRAP 104 effective 1 April 2025. Reference Group to continue into 2027-2029 work programme.
| Non-exchange Expenses |  |  |  | Local projects in progress:
| - Collective and individual goods and services |  | S Nondlazi |  | IPSAS 19 amendments issued. Effective since 1 January 2023. Included in Improvements to Standards of GRAP, 2026 - Board to approve March 2026.
| - Transfer expenses |  | S Nondlazi |  | IPSAS 48 issued. Effective 1 January 2026. Local project underway.
| Revenue |  | E van der Westhuizen |  | IPSAS 47 issued. Effective 1 January 2026. Research impact on GRAP in 2027 to 2029 work programme.
| Review of IPSAS 17 |  |  |  | IPSAS 45 issued. Effective 1 January 2025.
| - Heritage Assets |  | A Botha |  | GRAP 103 amended after post-implementation review, effective 1 April 2027. Consider IPSAS 45 guidance after amendments effective.
| - Infrastructure assets |  | S Nondlazi |  | The amendments related to infrastructure assets are included in the Improvements to Standards of GRAP, 2026 - Board to approve March 2026.
| Leases |  | A Botha |  | IPSAS 43 on Leases issued. Effective 1 April 2025. Local project included in 2027 to 2029 work programme.
| - Public sector specific leases | [9 empty] | Comment letter | Final IPSAS
| Limited scope review of Conceptual Framework (Measurement) |  | J Poggiolini / N Imam Shah |  | IPSAS amendments issued. Local ED 217 consultation in progress.
| Limited scope review of Conceptual Framework (next stage) |  | E van der Westhuizen |  | IPSAS amendments issued. Consider for a future work programme.
| Non-current assets held for sale |  | A Botha |  | IPSAS 44 issued. Effective 1 January 2025. No changes planned to local Standards.
| Borrowing costs |  | N Imam-Shah |  | Amendments to IPSAS published. Included in Improvements to Standards of GRAP, 2023. Effective date to be determined by Minister of Finance.
| Retirement Benefit Plans |  | Not applicable |  | IPSAS 49 approved in September 2023. Effective 1 January 2026. Not considerded relevant for local environment. |  | IPSAS
| - Exploration for and Evaluation of Mineral Resources |  | A Botha |  | IPSAS 50 approved. Effective 1 January 2027. No local project planned. Consider updating reference in Directive 5 for 2027/28. |  |  |  | ED |  | Comment letter | IPSAS
| - IFRIC 20, Stripping Costs in the Production Phase of a Surface Mine |  |  |  | Amendments to IPSAS 12 approved. Effective 1 January 2027. No local project planned. Consider updating reference in Directive 5 for 2027/28. |  |  |  | ED |  | Comment letter | IPSAS
| Startegy and work plan 2024 to 2028 |  | E van der Westhuizen |  | Final strategy and work plan approved. |  | ED | CED |  |  |  | Final strategy and workplan
| - Mid-period work programme consultation |  |  |  | Mid-period work programme consultation out for comment. Not a concurrent ED. Submit staff letter | [15 empty] | Comment letter
| IFRIC Alignment - limited scope |  | S Nondlazi |  | Final IPSAS approved December 2024. No impact on GRAP, IGRAPs already effective. | [7 empty] | IPSAS
ACTIVE AGENDA
| First Time Adoption of IPSAS (IPSAS 33) |  | A Botha |  | Monitor developments locally regarding the adoption of GRAP by departments. Amendments to IPSAS 33 approved September 2025. |  |  |  | ED |  | ED |  | Comment letter |  |  |  |  | IPSAS
| Public Sector Measurement |  | N Imam-Shah |  | IPSAS 46 issued. Effective 1 January 2025. Local project underway.
| - Application phase |  |  |  | Final amendments published. New phase introduced for COV in IPSAS 31. Expecting final approval September 2026. | [5 empty] | ED | CED | Comment letter |  |  |  | IPSAS | [5 empty] | IPSAS
| Improvements to IPSAS, 2023 |  | A Botha |  | Final Improvements, 2023 approved. Effective 1 April 2025 (IBOR reform) and 1 April 2026 (rest). IBOR reform included in Improvements to Standards of GRAP, 2023. Rest considered with Improvements to Standards of GRAP, 2026. |  | ED |  |  |  | Final IPSAS
| Improvements to IPSAS, 2025 |  | S Nondlazi |  | ED on Improvements to IPSAS, 2025 under development, approval expected March 2026. | [15 empty] | CED / Comment letter |  | IPSAS
| Natural resources |  | A Botha |  | IPSAS 51 approved Dec 2025. Effective 1 January 2028. No local project planned. Reassess in future work programme. | [6 empty] | ED | CED | Comment letter |  |  |  |  | IPSAS
| Presentation of financial statements |  | S Nondlazi |  | Consultation Paper and Illustrative Exposure Draft under development and expected to be approved March 2026. |  | PB | [13 empty] | CED | Comment letter
| GFSM alignment / IPSAS 22 update |  | N Imam-Shah |  | ED approved December 2025. Not a concurrent ED. May issue staff letter. | [13 empty] | ED |  | Potential comment letter
| Materiality |  | A Botha |  | Project brief approved March 2025.
| - Definition of Material - narrow-scope amendments to CF and IPSAS (phase 1) |  |  |  | Amendments phase 1 approved September 2025. | [10 empty] | ED | Comment letter | IPSAS
| - Making materiality judgements - limited scope (AFS) (phase 2) |  |  |  | ED approval expected March 2026, anticipate concurrent ED to be published in April 2026. | [15 empty] | CED | Comment letter
| - Making materiality judgements - limited scope (sustainability) (phase 3) |  |  |  | ED development to commence in 2026
| Post-implementation review IPSAS 20 Related Party Disclosures |  |  |  | To assess project direction March 2026.
Sustainability reporting standards
| Climate-related disclosures |  | N Imam-Shah |  | Comment letter submitted on concurrent exposure draft for ED 213. | [6 empty] | ED | CED | Comment letter
| - Own operations |  |  |  | IPSASB SRS 1 approved December 2025. | [13 empty] | SRS
| - Public Policy Programmes |  |  |  | Approval of IPSASB SRS expected December 2026. | [18 empty] | SRS
Recommended Practice Guidelines issued by the IPSASB
| - Long Term Sustainability of an Entity's Finances |  | E van der Westhuizen/N Imam-Shah |  | Amendments published.
| - Financial Statement Discussion and Analysis |  | E van der Westhuizen
| - Reporting on Service Performance Information |  | E van der Westhuizen/N Imam-Shah |  | Amendments published.
Other projects
| Amendments to the Cash Basis IPSAS |  | E van der Westhuizen |  | Monitor
Based on current IPSASB work programme.
Note: actions such as CED and related comment letter, and the publication of IPSAS are included in the quarter after the planned approval by the IPSASB given the delay in issuing the documents.
Note on AO61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not a concurrent exposure draft but will discuss with the Board in November 2025 and submit a staff letter
Note on AR61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not a concurrent exposure draft but will discuss with the Board in November 2025 and submit a staff letter

## IPSAS 33
IPSAS 33 |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
Address stakeholder concerns with IPSAS 33 to make it more user friendly and effective. This will be achieved by rearranging guidance by category and adding non-authoritative guidance and to clarify IPSAS 33’s role before the date of adoption, i.e. in the preparation phase; linking IPSAS 33 with the Pathways to Accruals.
Linkages with IPSASB or IASB projects
None.
Last history:
| Final IPSAS approved |  | 2025-09-01 |  | Approved
Current actions:
#1 | Project brief approved. |  | 2023-12-01 |  | Project brief approved
#2 | Exposure Draft approval. |  | 2024-06-01 |  | Exposure Draft approved | [5 empty] | ED
#3 | Secretariat to submit comment letter |  | Dec '24 |  | Comment letter submitted | [7 empty] | Comment letter
#4 | Final IPSAS approved |  | 2025-09-01 |  | Approved | [12 empty] | IPSAS
Planned communication:
None; not a concurrent ED.

## First Time Adoption of IPSASs (hidden)
| First Time Adoption of IPSASs | Decision dates |  | Status |  | Project milestones
[7 empty] | 2023/24 |  |  | 2024/25
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To review issued IPSAS 33 to assess if the requirements are appropriate for the first time adoption of Standards of GRAP by national and provincial departments.
Linkages with IPSASB or IASB projects
IPSAS 33 issued on First Time Adoption of Accrual Basis IPSASs.
Last history:
| Comment letter submitted to the IPSASB on proposed IPSASs when issued as part of the public consultation. |  | First quarter 2014.
| Monitor decisions to adopt GRAP at national and provincial departments, |  |  |  | Monitor.
Current actions:
#1 | Monitor developments locally. |  | Decision to monitor only - 2018
Planned communication:
#7 | None at present. |  |  |  | No actions.

## Public Sector Combinations (hidden)
| Public Sector Combinations | Decision dates |  | Status |  | Project milestones
2023/24
[6 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To provide comment on the proposed IPSASs on Public Sector Combinations.
Linkages with IPSASB or IASB projects
IPSASB project to develop accounting guidance for public sector combinations.
IASB research project on Business Combinations Under Common Control.
Last history:
| Comment letter submitted to the IPSASB on its Consultation Paper. |  | Late 2012.
| Comment letter issued to the IPSASB on the proposed IPSAS. |  | June 2016.
Based on the comments received on ED 138, the Board agreed not to revise GRAP 105-107 during the period 2017-2020. Included as a possible project in 2021-2023 work programme consultation.
| Board agreed to compare IPSAS 40 and GRAP 105-GRAP 107 to identify differences and if changes needed as part of the 2021-2023 work programme. |  | December 2019.
| Project brief approved. |  | September 2021. |  | Project brief approved.
| Exposure Draft approved |  |  |  | Exposure Draft approved.
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter issued.
#3 | Prepare a comparison of IPSAS 40 and GRAP 105-107
#4 | Prepare Exposure Draft of proposed amendments to GRAP 105-107 |  |  |  | Approved
#5 | Consult on Exposure Draft
Planned communication:
| To be developed when revisions made to GRAP 105-107. |  |  |  | To be decided.

## Social Benefits (hidden)
| Social Benefits | Decision dates |  | Status |  | Project milestones
2023/24
[6 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To provide comment on the IPSASB's Consultation Paper on Social Benefits.
Linkages with IPSASB or IASB projects
IPSASB project to develop accounting guidance for social benefits.
Last history:
Consultation Paper issued for comment.
| Exposure Draft issued for comment. |  | September 2017
| Final IPSAS issued. |  | December 2018
| Board agreed to add the development of a Standard of GRAP on Social Benefits to the work programme for 2021-2023. |  | December 2019
| Project brief approved for liocal project. |  | September 2020
| Initial project direction decided. |  | September 2021
Current actions:
#1 | Discuss project brief. |  | September 2021. |  | Revised.
#2 | Develop project proposal. |  | September 2021. |  | Initial direction decided.
#3 | Develop Issues Paper. |  |  |  | Second issues paper developed.
#4 | Develop Exposure Draft |  | September 2022 |  | Develop ED |  | LED
Planned communication:
#5 | After approval of the Exposure Draft

## Non-exchange Expenses (hidden)
| Non-exchange Expenses | Decision dates |  | Status |  |  | Project milestones
2023/24
[6 empty] | Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To provide comment on the proposed Consultation Paper on the accounting treatment of non-exchange expenses.
Linkages with IPSASB or IASB projects
Social benefits
Last history:
- Consultation Paper issued.
| - ED issued for collective and individual services and approved. |  | December 2019. |  | Approved.
| - ED issued on Transfer Expenses. |  | February 2020. |  | CED issued.
| - Comment letter issued. |  | October 2020. |  | Comment letter issued.
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | CED issued.
#3 | Comment letter issued. |  | June 2018 |  | Comment letter issued on CP.
| - Develop proposals for collective and individual goods or services. |  |  |  | Comment letter issued for collective and individual services
- Develop proposals for grants and other transfers
| - Publish concurrent Exposure Draft for proposed IPSAS (ED 72) and develop comment letter. |  | April 2020 |  | CED issued.
| - Comment letter issued. |  | October 2020 |  | Comment letter issused.
| - Issued Concurrent Exposure Draft of changes to ED 72. |  | December 2022 |  | IPSASB project in progress
#4 | IPSAS published |  | May 2023 |  |  | IPSAS
Project included in 2024-26 work programme
Planned communication:
#5 | Stakeholder communication plan developed for CED. |  | May 2020.

## Review of Revenue (hidden)
| Review of Revenue | Decision dates |  | Status |  |  |  | Project milestones
[6 empty] | 2022/23 |  | 2023/24
[6 empty] | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To provide comment on the proposed Consultation Paper on the review of the existing IPSASs 9, 11 and 23 on revenues from exchange transactions, revenue from construction contracts and revenue from non-exchange expenses, and the impact of IFRS 15 Contracts with Customers.
Linkages with IPSASB or IASB projects
IASB has issued IFRS 15 Contracts with Customers.
Last history:
Newly initiated project. Start date of project to be agreed by the IPSASB.
| ASB issued Research Paper on the Impact of IFRS 15 on Revenue in the Public Sector. |  | March 2015.
| SA Invited to participate in Task Based Group |  | June 2015
| Consultation Paper issued on revenue. |  |  |  | CED issued.
| Proposed IPSASs issued on revenue with performance obligations and revenue without performance obligations. |  | February 2020 |  | CED issued.
| Comment letter issued. |  | October 2020 |  | Comment letter issued.
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | CED issued
#3 | Comment letter issued on Consultation Paper |  |  |  | Comment letter issued.
- Revenue from contracts with customers
- Limited update of GRAP 23
- Grants and other transfers
#4 | Publish concurrent Exposure Draft of proposed IPSASs issued (ED 70 and ED 71) and developed comment letter. |  | Ápril 2020. |  | CED issued
#5 | Comment letter issued. |  | October 2020. |  | Comment leter issued.
#6 | Publish Concurrent Exposure Draft of proposed changes to ED 73 and develop comment letter. |  | December 2022 |  | In progress by IPSASB
#7 | IPSAS published |  | May 2023 |  |  | IPSAS
Review of revenue Standards included in 2024-26 work programme, subject to resource availability
Planned communication:
#8 | Stakeholder consultation plan developed. |  | May 2020.

## Public Sector Measurement (hidden)
| Public Sector Measurement | Decision dates |  | Status |  |  |  | Project milestones
[6 empty] | 2022/23 |  | 2023/24
[6 empty] | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Consider the effect of the IPSASB Conceptual Framework on the measurement requirements in existing IPSASs. |  | June 2015
Linkages with IPSASB or IASB projects
IPSASB project to develop principles to account for heritage assets.
Fair Value Measurement (IFRS 13), and Unit of Account projects of IASB.
Last history:
Newly initiated project.
| Consultation Paper and Exposure Draft issued. |  | March 2019. |  | Comment letter issued.
| Exposure Draft approved by the IPSASB. |  | March 2021 |  | Exposure Draft approved.
| Comment letter issued. |  | September 2021 |  | Comment ltetter issued.
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter issued on CP and illustrative ED.
#3 | Monitor developments after initial consultation to assess if amendments needed to GRAP.
#4 | Issue concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter issued.
#5 | IPSAS published |  | May 2023 |  |  | IPSAS
Planned communication:
#6 | Project included in work programe for 2024-2026.

## Heritage Assets (hidden)
| Heritage Assets | Decision dates |  | Status |  |  | Project milestones
2023/24
[6 empty] | Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Develop principles to account for heritage assets. |  | June 2015
Linkages with IPSASB or IASB projects
IPSASB project to develop principles to account for heritage assets.
Last history:
Newly initiated project.
| Based on feedback received on ED 138, Board agreed to undertake a post-implementation review of GRAP 103 in 2019, before making decisions about any revisions to GRAP 103. Agree to monitor international project. |  | June 2016. |  | Monitor
| Consultation Paper issued. |  |  |  | Comment letter issued.
| Exposure Draft issued by the IPSASB. |  | March 2021 |  | Exposure Draft approved.
| Comment letter issued. |  | September 2021 |  | Comment letter issued.
Current actions:
#1 | Monitor developments on project. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter issued.
#3 | Undertake post-implementation review of existing GRAP103 in 2019 and decide if alignment necessary with proposed changes to IPSAS 17. |  |  |  | GRAP 103 revised; awaiting approval of Minister of Finance
| Amended IPSAS published |  | 2023
Planned communication:
#4 | Will consider changes to IPSAS 17 as part of improvements cycle during 2024-2026.

## Infrastructure Assets (hidden)
| Infrastructure Assets | Decision dates |  | Status |  |  | Projetc milestones
2023/24
[6 empty] | Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Develop guidance on selected aspects of IPSAS 17 in accounting for infrastructure assets. |  | June 2015
Linkages with IPSASB or IASB projects
IPSASB project to develop guidance on accounting for infrastructure assets.
Last history:
Newly initiated project.
| Project brief approved. |  | June 2019. |  | Project brief approved.
| Exposure Draft approved by the IPSASB. |  | March 2021 |  | Exposure Draft approved.
| Comment letter issued. |  | September 2021 |  | Comment letter issued.
| Amendments to IPSAS on PPE published |  | 2023
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter isssued
#3 | Monitor developments after initial consultation to assess if amendments needed to GRAP 17.
Planned communication:
#4 | Amendments related to Measurement to be included in work programme for 2024-2026.

## Leases (hidden)
| Leases | Decision dates |  | Status |  | Project milestones
2023/24
[6 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| To review the requirements in IFRS 16 on Leases and how the Standard is adopted by IPSASB. |  | February 2016.
Linkages with IPSASB or IASB projects
| IPSASB project to review IFRS 16 and its existing Standard on leases. Will include consideration of leases of assets at no or nominal value, as well as changing the lessor accounting. |  | June 2016.
Last history:
| Project brief approved. |  | June 2016.
| Proposed IPSAS on leases issued for comment. |  |  |  | Comment letter issued.
IPSAS on Leases published
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings and Task Force. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter issued.
#3 | Public sector leases |  |  |  | Proposed IPSAS being developed. |  |  |  | IPSAS
Planned communication:
#4 | For 2027-2029 work programme consultation

## Measurement application phase
Measurement - Application Phase |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Proposed amendments to IPSAS to consider applicability of current operational value. IPSASB agreed the potential application of COV across the existing suite of IPSAS should be added to the work program as a separate phase, with work to begin after the expected approval of IPSAS 46 Measurement. |  | 2022-12-01 |  | Project scope agreed
Linkages with IPSASB or IASB projects
IPSAS 46, Measurement
Last history:
| Approve final IPSAS guidance, excluding intangibles. |  | 2025-06-01 |  | Approved June 2025
Current actions:
#1 | Project scope agreed |  | 2022-12-01 |  | Project scope agreed
#2 | Exposure Draft approval. |  | 2024-06-01 |  | Exposure Draft for approval |  | ED
#3 | Issue concurrent ED |  | 2024-08-01 |  | Issue Concurrent Exposure Draft |  |  | CED
#4 | Secretariat to submit comment letter |  | Dec 24 |  | Comment letter submitted |  |  |  | Comment letter
#5 | Approve final IPSAS guidance, excluding intangibles |  | 2025-06-01 |  | Approved June 2025 | [7 empty] | IPSAS
#6 | Assess next steps for COV in IPSAS 31 Intangible Assets |  |  |  | Final approval expected Sept 2026 | [12 empty] | IPSAS
Planned communication:

## Public sector specific leases (hidden)
Public sector specific leases |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  | 2024/25
[7 empty] | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Develop additional guidance identifying and addressing lease-related accounting issues associated with public sector lease-type arrangements. |  |  |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSAS 43 Leases
Last history:
| Final approval of pronouncement (including BCs) |  | 2024-09-01 |  | Final guidance including BCs approved
Project actions:
#1 | Monitor developments and provide input through the IPSASB's meetings and Task Force. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft on ED 84 and develop comment letter. |  |  |  | CED published and Comment letter issued.
#3 | Not issue concurrent Exposure Draft on ED 88; Secretariat to submit a comment letter. |  | May '24 |  | Comment letter issued. | [5 empty] | Comment letter
#4 | Final public sector leases approved and published (amendments to existing IPSAS) |  | June '24 |  | Amendments to IPSAS approved
#5 | Final approval of pronouncement (including BCs) |  | 2024-09-01 |  | BCs approved | [7 empty] | IPSAS
Planned communication:
None

## Improvements
Improvements project |  | Decision dates | Status |  | Project milestones
[5 empty] | 2023/24 |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[6 empty] | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To provide comment on the proposed Improvements to IPSAS and include in equivalent ASB Improvements Project.
Linkages with IPSASB or IASB projects
IASB Improvements and narrow scope amendments.
Last history:
| Improvements to IPSAS 2025 under development. |  |  | ED under development
Current actions:
#1 | Approve Exposure Draft on Improvements to IPSAS, 2025. |  |  | Approval expected March 2026 | [14 empty] | ED
#2 | Publish concurrent Exposure Draft (if considered relevant). | [17 empty] | CED
#3 | Submit comment letter |  |  |  |  | Comment letter | [12 empty] | Comment letter
#4 | Approve final Improvements |  |  | Approval expected September 2026 | [16 empty] | IPSAS
Planned communication:
#5 | Dependent on whether concurrent ED published

## Natural Resources
Natural Resources |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 2 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Develop a Consultation Paper, then one or more Exposure Drafts to address the issues relating to the recognition, measurement, presentation and disclosure of natural resources. |  | March 2020 |  | Project brief approved
Linkages with IPSASB or IASB projects
IFRS 6, Exploration for and Evaluation of Mineral Resources; IFRIC 20, Stripping Costs in the Production Phase of a Surface Mine
Last history:
| IPSAS 50 on Exploration for and Evaluation of Mineral Resources and amendments to IPSAS 12 Inventory for Stripping Costs in the Production Phase of a Surface Mine approved |  | Sept 2024 |  | IPSAS 50 approved |  |  |  |  | Comment letter
| IPSAS 51 on Tangible Natural Resources Held for Conservation approved |  | Dec 2025 |  | IPSAS 51 approved | [5 empty] | ED
Current actions:
#1 | Approval of Project brief |  | March 2020 |  | Project brief approved
#2 | Approval of Consultation Paper, comment letter submitted to IPSASB |  | March 2022 |  | Comment letter submitted
#3 | Approval of Exposure Drafts 86 and 87: IFRS 6 and IFRIC 20 aligned guidance |  | December 2023 |  | EDs issued |  |  | ED
#4 | Submit comment letters on ED 86 and ED 87 |  | May 2024 |  | Comment letters submitted |  |  |  |  | Comment letter
#5 | Approval of Final IPSAS, Exploration for and Evaluation of Mineral Resources, and amendments to IPSAS 12 Stripping Costs in the Production Phase of a Surface Mine |  | Sept 2024 |  | IPSAS approved | [5 empty] | IPSAS
#6 | Approval of Exposure Draft: Natural Resources |  | Sept 2024 |  | ED approved | [5 empty] | ED
#7 | Issue Concurrent Exposure Draft on Natural Resources |  | Oct 2024 |  | CED published | [6 empty] | CED
#8 | Comment letter on Exposure Draft on Natural Resources |  | Feb 2025 |  | Comment letter submitted | [7 empty] | Comment letter
#9 | Approval of Final IPSAS on Tangible Natural Resources |  | Dec 2025 |  | IPSAS 51 approved | [12 empty] | IPSAS
Planned communication:
| Articles to be published |  |  |  | Ongoing

## Presentation of FS
Presentation of Financial Statements |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Enhance communication of financial information by replacing IPSAS 1 Presentation of Financial Statements to help all public sector entities communicate their financial information better. |  | September 2023 |  | Project brief approved
Linkages with IPSASB or IASB projects
IASB communication in financial reporting
Last history:
#1 | Approval of Project brief |  | September 2023 |  | Project brief approved
Current actions:
#1 | Approval of Project brief |  | September 2023 |  | Project brief approved
#2 | Development and approval of Consutlation Paper and Illustrative Exposure Draft |  | ED expected to be approved March 2026 |  | Ongoing
#3 | Issue Concurrent Exposure Draft of CP | [19 empty] | CED
#4 | Submit comment letter | [20 empty] | Comment letter
#5 | Development and approval of Exposure Draft
#6 | Issue Concurrent Exposure Draft
#7 | Submit comment letter
Planned communication:
TBD once concurrent Exposure Draft published

## Materiality
Materiality |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Three-fold: #1 - Align definition of "material" across IPSAS literature. #2 - Develop guidance on applying materiality to financial statements. #3 - Develop guidance on applying materiality to sustainability reporting. |  | March 2025 |  | Project brief approved
Linkages with IPSASB or IASB projects
IASB Conceptual Framework and narrow-scope amendments on materiality. IASB Practice Statement on materiality.
Last history:
#1 | Issue amendments to IPSAS (phase 1) |  | September 2025 |  | Approved
Current actions:
#1 | Approval of Project brief |  | March 2025 |  | Project brief approved
#2 | Approve Exposure Draft - definition of material (narrow-scope amendments) |  | March 2025 |  | ED approved | [5 empty] | ED
#4 | Submit comment letter (staff) | [10 empty] | Comment letter
#5 | Issue amendments to IPSAS (phase 1) |  | September 2025 |  | Approved | [7 empty] | IPSAS
#6 | Develop and approve ED - making materiality judgements practice statement (phase 2) |  | Approval expected March 2026 | [12 empty] | ED
#7 | Issue concurrent ED | [14 empty] | CED
#8 | Submit comment letter | [15 empty] | Comment letter
Planned communication:
TBD once concurrent Exposure Draft published

## IPSAS 20 review
PIR of IPSAS 20 |  | Decision dates | Status |  | Project milestones
[5 empty] | 2025/26 |  | 2026/27
Quarter 1
[6 empty] | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
The IPSASB's first (pilot) post-implementation review will be on IPSAS 20 Related Party Disclosures, to assess whether the Standard is reaching its intended objectives
Linkages with IPSASB or IASB projects
None
Last history:
#1
Current actions:
#1 | Consider project direction |  |  | To assess project direction at March 2026 meeting
#2
#3
#4
#5
#6
#7
Planned communication:

## Climate related dislosure
Sustainability - Climate-related disclosures |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Develop a standard that provides public sector specific guidance on climate-related disclosures. |  | 2023-06-01 |  | Project brief approved
Linkages with IPSASB or IASB projects
IFRS S1 and IFRS S2
Last history:
| Approval of IPSASB SRS 1 Climate-related Disclosures |  | December 2025 |  | SRS 1 Approved
Current actions:
#1 | Approval of Project brief |  | 2023-06-01 |  | Project brief approved
#2 | Development and approval of Exposure Draft |  | Sept '24 |  | Exposure Draft approved | [6 empty] | ED
#3 | Issue Concurrent Exposure Draft |  | Oct '24 |  | CED issued | [7 empty] | CED
#4 | Submit comment letter |  | Feb '25 |  | Comment letter submitted | [8 empty] | Comment letter
#5 | Review responses and approve final SRS: Own operations |  | December 25 |  | SRS 1 Approved | [13 empty] | SRS
#6 | Review responses and approve final SRS: Public Policy Programmes |  | Anticipated December 2026 | [19 empty] | SRS
Planned communication:
Ongoing
Note on B38: Elizna van der Westhuizen: No new ED has been planned at this stage

## NCAHFS (hidden)
| Non-current assets held for sale | Decision dates |  | Status |  |  | Project milestones
[6 empty] | 2022/23 |  |  | 2024/24
[6 empty] | Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1
Objective:
To undertake a limited scope review of the Conceptual Framework.
Linkages with IPSASB or IASB projects
IPSASB projects on measurement.
Last history:
| Project brief approved. |  | June 2020.
| Exposure Draft approved. |  | March 2021
| Comment letter issued. |  | September 2021. |  | Comment letter issued.
ÍPSAS issued.
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft and develop comment letter. |  |  |  | Comment letter issued.
Planned communication:
#4 | Final IPSAS issued - not currently included in ASB's work programme.

## Conceptual Framework (hidden)
| Limited scope review of the Conceptual Framework | Decision dates |  | Status |  |  | Project milestones
[6 empty] | 2022/23 |  | 2023/24
[6 empty] | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To undertake a limited scope review of the Conceptual Framework.
Linkages with IPSASB or IASB projects
IASB conceptual framework.
Last history:
| Project brief approved. |  | March 2020.
| Exposure Draft issued. |  | March 2021
| Comment letter issued. |  | September 2021. |  | Comment letter issued.
Current actions:
#1 | Monitor developments and provide input through the IPSASB's meetings. |  |  |  | Monitor
#2 | Publish concurrent Exposure Draft for changes to measurement and develop comment letter. |  |  |  | Comment letter issued. | Framework
#3 | Publish concurrent Exposuire Draft for changes to other matters and develop comment letter. |  |  |  | Comment letter issued. |  |  | Framework
Planned communication:
#4 | Measurement related changes included in ASB 2024-2026 work programme.

## Service Performance Information (hidden)
| Reporting on Service Performance Information | Decision dates |  | Status
Objective:
To assess if, and how, reporting of service performance achievements could be enhanced based on international best practice.
Linkages with IPSASB or IASB projects
RPG 3 issued by the IPSASB on Reporting Service Performance Information.
Last history:
| Board agreed to consider how to deal with this reporting once the review of the mandate is completed. |  | March 2015
Current actions:
#1 | - Review of ASB's mandate to expand it to reporting outside the financial statements. |  |  |  | Engagement with stakeholders

## Finanical Statement Discussion (hidden)
| Financial Statement Discussion and Analysis | Decision dates |  | Status
Objective:
To assess if, and how, the preparation of a financial statement discussion and analysis to accompany the financial statements could be inroduced.
Linkages with IPSASB or IASB projects
RPG 2 issued by the IPSASB on Financial Statement Discussion and Analysis.
Last history:
| Secretariat presented an analysis of the existing reporting requirements prescribed by the National Treasury in the annual report against the requirements of RPG 2 to assess alignment. |  | June 2014.
| Board agreed to consider how to deal with this reporting once the review of the mandate is completed. |  | September 2014.
Current actions:
#1 | Review of ASB's mandate to expand it to reporting outside the financial statements. |  |  |  | Engagement with stakeholders

## LT Sustainability of Finances (hidden)
| Long Term Sustainability of an Entity's Finances | Decision dates |  | Status
Objective:
To assess if, and how, reporting on the long term sustainability of an entity's finances could be introduced into reporting outside the financial statements.
Linkages with IPSASB or IASB projects
RPG 1 issued by the IPSASB on The Long Term Sustainabilty of an Entity's Finances.
Last history:
| Board agreed to consider how to deal with this reporting once the review of the mandate is completed. |  | September 2014.
Current actions:
#1 | Review of ASB's mandate to expand it to reporting outside the financial statements. |  |  |  | Engagement with stakeholders