## Work programme
WORK PROGRAMME FOR THE PERIOD ENDING 31 MARCH 2028
[5 empty] | 2023/24 | [11 empty] | 2026/27 |  |  |  |  | 2027/28
| PROJECT | SECRETARIAT | CURRENT STATUS | 2022/23 |  |  |  |  | 2024/25 |  |  |  | 2025/26
|  |  |  | QUARTER 4 | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 |  | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 |  | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4
|  |  |  | (January to March 2023) | (April to June 2023) | (July to September 2023) | (October to December 2023) | (January to March 2024) | (April to June 2024) | (July to September 2024) | (October to December 2024) | (January to March 2025) | (April to June 2025) | (July to September 2025) | (October to December 2025) | (January to March 2026) |  | (April to June 2026) | (July to September 2026) | (October to December 2026) | (January to March 2027) |  | (April to June 2027) | (July to September 2027) | (October to December 2027) | (January to March 2028)
MAINTAIN AND ENHANCE EXISTING STANDARDS OF GRAP AND DEVELOP NEW STANDARDS WHERE GAPS ARE IDENTIFIED
Local initiatives
| Going concern and the liquidation basis of accounting | A Botha | Effective date regulated as 1 April 2027 | Submission
Maintenance of Standards
| GRAP Reporting Framework | S Nondlazi | Reporting Framework for 2026/27 approved |  |  | Annexure | Communication | LED | Communication | Comments | Communication |  |  | Annexure | Communication |  |  |  | Annexure | Communication
|  | A Botha | 2027/28 to be developed | [20 empty] | Annexure | Communication
| Improvements to the Standards of GRAP (2022) | N Imam Shah | Effective date regulated as 1 April 2028 |  | Consult | GRAP | Submission Communication
| Improvements to the Standards of GRAP (2026) | S Nondlazi | Improvements, 2026 approved | [10 empty] | LED | Communication | Comments |  | Communication
[16 empty] | GRAP |  | Submission
Research
| Literature review of employee benefits | N Imam Shah | Project brief to be approved | [22 empty] | IP
Other
| Work programme for 2027 to 2029 | E van der Westhuizen | Work programme 2027 - 2029 approved | [6 empty] | LED |  |  | Final WP | Communication
| Work programme for 2030 - 2032 | S Nondlazi | To develop consultation | [19 empty] | ED |  |  | WP
Convergence with IPSASB
| Social benefits | E van der Westhuizen | Final Standard approved Development of transitional provisions underway |  |  | ED GRAP |  |  | Issues Paper |  |  | Comments | LED | Communication |  | Comments |  | Communication
| - Transitional provisions |  |  |  |  | Communication | [5 empty] | GRAP |  |  |  | GRAP |  |  |  | LED | Communication |  |  | GRAP | Communication
| - Consolidation of Directives | [18 empty] | IP
| Comparison with IPSAS 40 on Public Sector Combination | A Botha | Effective date regulated as 1 April 2027 | ED GRAP |  |  | Comments | Submission Communication
| Measurement | N Imam Shah | Amendments to Conceptual Framework approved |  |  | PB |  |  |  |  | IP
| - Amendments to Conceptual Framework | [13 empty] | LED | Communication |  |  | Comments
[19 empty] | CF | Communication
| - Standard of GRAP on Measurement | [19 empty] | LED |  | Communication |  | GRAP | Communication
| Transfer Expenses | S Nondlazi | Development of issues paper underway. Next steps to be considered December 2026 [**new project brief to be developed for next steps] | [16 empty] | IP |  |  | TBD | TBD | TBD | TBD
| Revenue | A Botha | Project brief to be approved | [21 empty] | IP
| Sustainability-related uncertainties in the financial statements | N Imam Shah | To be determined from IPSASB next improvements project | [19 empty] | TBD | TBD | TBD | TBD
Convergence with IASB
| No IASB convergence projects ongoing |  |  | Communication |  | GRAP | Communication
Reviews of Standards
| Post-implementation review of GRAP 103 on Heritage Assets (amendments to GRAP 103) | A Botha | Effective date regulated as 1 April 2027
| Post-implementation review of GRAP 109 on Accounting by Principals and Agents | E van der Westhuizen | Review Report approved | Consult | Consult | Consult |  | Comments |  | Draft RR
| - Amend GRAP 109 on Accounting by Principals and Agents | A Botha | Final amendments approved | [10 empty] | LED | Communication |  |  | Comments | Submission
[18 empty] | GRAP | Communication
| Post-implementation review of GRAP 108 on Statutory Receivables | A Botha | Review Report approved |  |  | Issues Paper | LED | [5 empty] | Comments |  | Draft RR | Communication
| Review of GRAP 20 on Related Party Disclosures | S Nondlazi | Review Report approved Amendment of GRAP 20 included in Improvements, 2026 |  |  | PB |  |  | Results of Review |  | Draft RR
| Review of GRAP 18 on Segment Reporting | N Imam Shah | Result of review to be considered | [12 empty] | Results of Review |  |  |  | Draft RR
PROMOTE A CULTURE OF LEARNING WITH PREPARERS AND USERS OF THE FINANCIAL STATEMENTS
| Education material for preparers of financial statements | All | Material recorded for YouTube |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan
| GRAP 104 Financial Instruments reference group | N Imam Shah | Outputs per separate work programme |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan
| GRAP 111 Social Benefits reference group | E van der Westhuizen | Establish after approval of transitional provisions | [21 empty] | Outputs per plan | Outputs per plan
Abbreviations
| GRAP Reporting Framework Annexure | Annexure
| Local exposure draft of new or amended Conceptual Framework, Standard of GRAP, Interpretation, Directive or Guideline | LED
| Final Standard | GRAP
| Final Conceptual Framework | CF
| Final Directive | FD
| Final Interpretation | IGRAP
| Final Guideline | FG
| Comments on exposure draft considered by Board | Comments
| Submission to the Minister of Finance | Submission
| Concurrent exposure draft (with IPSASB) | CED
| Comment letter to the IPSASB or IASB | Comment letter
| Project brief | PB
| Draft Research Paper | Draft RP
| Draft Review Report | Draft RR
| Issues Paper | IP
| Communication on pronouncements | Communication
Note on AY9: Elizna van der Westhuizen: Meeting is in July 2026
Note on BK9: Elizna van der Westhuizen: Can incorporate discussion with new Board on direction of travel, projects in progress.
Note on AM10: Elizna van der Westhuizen: Meeting is scheduled for July 2025
Note on R54: Elizna vdW: July 2023
Note on R104: Elizna vdW: July 2023

## GRAP Reporting Framework
GRAP Reporting Framework |  | Decision dates |  | Status |  | Project milestones
[11 empty] | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
2023/24
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To prescribe the proposed GRAP Reporting Framework for each reporting period.
| Based on results of ED 138, continue to publish ED 138, but no need to consult every year on changes to the Annexures. |  | June 2016.
Linkages with IPSASB or IASB projects
None.
Last history/project status:
| Reporting Framework for 2026/27 approved |  | Sept '25 |  | 2026/27 reporting framework approved.
Project actions:
#1 | Approve Reporting Framework for 2026/27 |  | Sept '25 |  | 2026/27 reporting framework approved. |  |  |  |  | LED |  | Communication | [5 empty] | Annexure 2026/27 | Communication
| Approve Reporting Framework for 2027/28 | [20 empty] | Annexure 2027/28 | Communication
Approval of effective dates:
September each year in advance of commencement of affected reporting period.
Transitional provisions:
None.
Planned communication:
#2 | Articles, communication to CFOs, presentations |  |  |  | Ongoing |  |  |  | Communication

## Improvements
Improvements to Standards of GRAP |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
Align Standards of GRAP with latest IPSASB improvements, and IASB improvements and narrow scope amendments.
Linkages with IPSASB or IASB projects
IPSASB improvements project, and IASB improvements project and narrow scope amendments (see IASB tracking table).
Last history/project status:
| Improvements, 2023 and IGRAP 22 approved. |  | September 2023 |  | Approved
| Submission made to the Minister of Finance for Improvements, 2023 |  | December 2023 |  | Effective date of 1 April 2028 published for comment
| Improvements to Standards of GRAP, 2026 approved |  | 2026-03-01 |  | Approved
Project actions:
#1 | Develop Exposure Draft of proposed Improvements (2026) |  | 2025-09-01 |  | Exposure Draft approved | [12 empty] | LED | Communication
#2 | Collate and analyse feedback and finalise amendments. Approve final Improvements, 2026 |  | 2026-03-01 |  | Approved |  |  | GRAP and IGRAP | [11 empty] | GRAP |  | Communication
#3 | Make submission to the Minister of Finance for Improvements (2026). | [7 empty] | Submission | [12 empty] | Submission
#4
#5
Planned communication:
#6 |  |  | Ongoing |  | Ongoing |  |  |  | Communication

## Whole of Government Accounts (hidden)
| Whole of Government Consolidation | Decision dates |  | Status |  |  | Project milestones
2016/17
[6 empty] | Quarter 3 |  | Quarter 4 | Quarter 1
Objective:
| Position Paper to be developed by the OAG. Project arose from trilateral strategy for 2014 to 2016. |  | July 2014.
| Based on results on ED 138, decision to (1) identify current issues in preparing national and provincial consolidated financial statements, and (2) develop guidance on combined financial statements. Both projects will be undertaken in the 2017-2020 cycle. |  | June 2016.
Linkages with IPSASB or IASB projects
None
Last history:
| Position Paper to be developed by the OAG and presented to the trilateral meeting. |  | January 2015.
| ASB to undertake research in identifying issues in national and provincial consolidations, and develop guidance on combined financial statements for 2017-2020 cycle. |  | June 2016.
Current actions:
#1 | Develop project brief for identifying issues with current national and provincial consolidations. |  | August 2016. |  | Research | PB

## Citizens Reporting (hidden)
| A Citizen's Guide to Reporting | Decision dates |  | Status |  | Project milestones
[5 empty] | Quarter 3 | Quarter 4 | Quarter 1
Objective:
| To develop intergrated, plain language reporting for citizens to understand what was planned in the strategy, what resources were budgeted, how those resources were used, and what was achieved. |  | July 2014.
Linkages with IPSASB or IASB projects
None.
Last history:
| Agreed as part of trilateral strategy for 2014-2016. |  | July 2014.
| Board agreed to postpone project as part of the review of the mandate, and the possibility to expand the mandate of the ASB to reporting outside the financial statements |  | September 2014.
| Based on results on ED 138, agreed to undertake research on the need for this type of reporting. This will be commenced in the 2017-2020 cycle. |  | June 2016.
Current actions:
#1 | None at present.

## Cash Flow Statements (hidden)
| Cash Flow Statements | Decision dates |  | Status |  | Project milestones
2016/17
[5 empty] | Quarter 3 |  | Quarter 4 | Quarter 1
Objective:
| To review the presentation of specific cash flows, e.g. grants related to capital expenditure, as a result of comments received as part of the post-implementation review. |  | March 2014.
Linkages with IPSASB or IASB projects
IASB projects on (a) Disclosure Initiative - Principles of Disclosures; and (b) Proposed Narrow Scope Amendments to IAS 7.
Last history:
| Proposed review added to the work programme as a result of the post-implementation review. |  | March 2014.
| Based on feedback on ED 138, decision to undertake further work on the format of the cash flow statements. Decision to postpone any work on this area to the 2017-2020 cycle. |  | June 2016.
Current actions:
#1 | Assess possible changes during the 2017-202 cycle.

## Social benefits
Social benefits |  | Decision dates |  | Status |  |  |  | Project milestones
Project milestones
[8 empty] | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2026/27
[14 empty] | Quarter 2 |  |  | Quarter 1 | Quarter 2
[6 empty] | Quarter 1 |  |  | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Develop a Standard of GRAP on Social Benefits. Use IPSAS 42 on Social Benefits as a starting point and modify for local environemnt. |  | September 2020 |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSAS 42 on Social Benefits
Last history/project status:
| Standard of GRAP on Social Benefits approved |  | 2026-03-01 |  | Approved
Project actions:
#1 | Discuss and reconfirm project brief. |  | September 2021 |  | Amended
#2 | Develop project proposal to progress project (convergence versus departure) |  | September 2021 |  | Direction agreed
#3 | Develop an Issues Paper outlining key issues on IPSAS 42 and its application locally. |  | 2022-03-01 |  | Direction agreed
#4 | Develop Exposure Draft |  | 2023-07-01 |  | Exposure Draft approved |  |  |  | LED
#5 | Comment deadline extended |  | Dec '23 |  | Comment deadline extended
#6 | Issues Paper discussed |  | 2024-07-24 |  | Issues considered
#7 | Collate and analyse feedback and finalise amendments. |  | 2025-03-25 |  | Review of responses | [10 empty] | Comments
#8 | Re-expose ED 205 as ED 214: approval of ED |  | 2025-07-01 |  | Exposure Draft approved
#9 | Collate and analyse feedback and finalise amendments. Approve final Standard of GRAP |  | 2026-03-01 |  | Approved
#10 | Next phase: develop transitional provisions and proposed effective date | [17 empty] | LED | Communication
#11 | Consider consolidation of Directives | [17 empty] | IP
Planned communication:
#12 | [9 empty] | Communication

## Review of IPSAS 40
Review of IPSAS 40 on Public Sector Combinations |  | Decision dates |  | Status |  | Project milestones | [20 empty] | Project Milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
[22 empty] | Quarter 2 |  |  | Quarter 1 |  | Quarter 2 |  |  | Quarter 1 | Quarter 2
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Compare IPSAS 40 to GRAP 105 to GRAP 107 on transfers of functions and mergers. Identify what differences exist (if any), and decide if any amendments are needed to the Standards of GRAP. |  | September 2021. |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSAS 40 on Public Sector Combinations
Last history/project status:
| Submission made to Minister of Finance |  |  |  | Submission made
Project actions:
#1 | Develop amendments for Exposure draft. Exposure Draft approved. |  | September 2022 |  | ED approved.
#2 | Consult with stakeholders |  |  |  | Concluded |  | Communication
#3 | Collate and analyse feedback and finalise amendments. Approve final amendments to Standards of GRAP |  | 2023-12-01 |  | Approval |  |  |  | Comments and GRAP
#4 | Develop submission to the Minister on the proposed effective date |  |  |  | Regulated as 1 April 2027 |  |  |  |  | Submission |  | Submission in progress |  |  |  |  | LED
Planned communication:
#5 | Opportunites to present approved changes identified on an ongoing basis. |  |  |  | Communication |  |  |  |  | Communication
Comments
LED
Communication

## Measurement
Measurement |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| (i) Amend the Chapter on Measurement of Assets and Liabilities in the Conceptual Framework, based on amendments to the IPSASB Conceptual Framework. (ii) Develop a Standard of GRAP on Measurement by considering IPSAS 46 on Measurement. |  | 2023-09-01 |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSASB Conceptual Framework; IPSAS 46 Measurement
Last history/project status:
| Develop Exposure Draft: Amendments to Conceptual Framework |  | November '25 |  | Exposure Draft approved
Project actions:
#1 | Approval of Project brief |  | September 2023 |  | Approved
#2 | Research and develop issues paper and agree approach to develop Exposure Drafts |  | Dec '24 |  | Approach agreed |  | Communication | [6 empty] | Issues Paper
#3 | Amended approach approved |  | July '25 |  | Approach amended
#4 | Develop Exposure Draft: Amendments to Conceptual Framework |  | November '25 |  | Exposure Draft approved | [13 empty] | LED | Communication
#5 | Analyse responses to ED | [20 empty] | Comments
#6 | Approve amendments to CF | [20 empty] | CF | Communication
#7 | Develop Exposure Draft: Standard of GRAP on Measurement | [22 empty] | LED
#8 | Analyse responses and approve amendments to CF
Planned communication:
#9 | Awareness of discussion of issues with stakeholders, presentation on website |  | Ongoing

## Transfer expenses
Transfer expenses |  | Decision dates |  | Status |  |  |  | Project milestones
Project milestones
[8 empty] | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  | 2026/27
[14 empty] | Quarter 2 |  |  | Quarter 1 | Quarter 2 |  |  | Quarter 1 | Quarter 2
[6 empty] | Quarter 1 |  |  | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Research issues and establish whether there is a need for a Standard of GRAP on Transfer Expenses. If so, consider appropriateness of IPSAS 48 Transfer Expenses for local environment. |  | September 2024 |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSAS 48 Transfer Expenses
Last history/project status:
| Project brief approved |  | September 2024 |  | Project brief approved
Project actions:
#1 | Research and develop issues paper; decide next steps. |  |  |  | Research in progress | [17 empty] | IP
Planned communication:
#2 | Communication on research in initial phase |  |  |  | Once project started |  |  |  |  | Communication

## Review of GRAP 109
Review of GRAP 109 on Accounting by Principals and Agents |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 | [5 empty] | 2025/26 |  |  |  |  | 2026/27
[13 empty] | Quarter 2 |  |  |  | Quarter 1 | Quarter 2 |  |  |  | Quarter 1 |  | Quarter 2
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  |  | Quarter 3 | Quarter 4 |  |  |  | Quarter 3 | Quarter 4 |  |  |  |  | Quarter 3 | Quarter 4
Objective:
#1 | Undertake a post-implementation review of GRAP 109. |  | September 2021 |  | Project brief approved
#2 | Amend GRAP 109 |  | 2024-09-01 |  | Project brief approved
No links with international projects.
Last history/project status:
| Approve Exposure Draft |  | 2025-09-01 |  | Exposure Draft approved
Project actions:
Phase 1: post-implementation review
#1 | Develop Project brief. |  | September 2021 |  | Project brief approved
#2 | Phase 1 of review completed. |  | May 2022 |  | Phase 1 completed
#3 | Develop consultation document. |  | November 2022 |  | ED approved |  | Consult | Consult
#4 | Collate and analyse feedback and make recommendations to the Board. |  | 2024-04-01 |  | Results of Review approved |  |  |  |  | Results of review
#5 | Communicate outcomes of review and actions agreed by the Board. |  | 2024-09-01 |  | Review Report approved | [8 empty] | Review Report
Phase 2: amend GRAP 109
#6 | Develop project brief to amend GRAP 109 |  | 2024-09-01 |  | Project brief approved
#7 | Develop responses to actions agreed by the Board: Exposure Draft to amend GRAP 109 |  | 2025-09-01 |  | Exposure Draft approved | [13 empty] | LED | Communication
#8 | Collate and analyse feedback and finalise amendments. | [21 empty] | Comment
#9 | Approve final amendments to Standard of GRAP | [21 empty] | GRAP
#10 | Submission to Minister of Finance | [23 empty] | Submission
Planned communication:
#11 | Communication on ED - articles, presentation |  |  |  | Ongoing

## Review of GRAP 108
Review of GRAP 108 on Statutory Receivables |  | Decision dates |  | Status |  | Project milestones | [9 empty] | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2023/24 |  |  |  |  | 2025/26 | [6 empty] | 2026/27
[13 empty] | Quarter 2 | [9 empty] | Quarter 1 |  | Quarter 2 |  |  | Quarter 1 | Quarter 2
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  |  |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Undertake a post-implementation review of GRAP 108. |  | September 2021 |  | Project brief approved
No links with international projects.
Last history/project status:
| Communicate outcomes of review and actions agreed by the Board. |  | November '25 |  | Review Report approved
Reconsider impairment model once practice with ECL established from GRAP 104
Project actions:
#1 | Develop Project brief. |  | September 2021 |  | Project brief approved
#2 | Develop consultation document. |  | 2023-12-01 |  | Consultation document approved |  |  | Issues Paper | Consultation document | [8 empty] | Issues Paper | Consultation document
#3 | Collate and analyse feedback and approve next steps. |  | July 2025 |  | Next steps approved | [18 empty] | Comments
#4 | Communicate outcomes of review and actions agreed by the Board. |  | November '25 |  | Review Report approved | [20 empty] | Review Report | Communication
#5 | Develop responses to actions agreed by the Board. |  |  |  | FAQ issued
Planned communication:
#6 |  |  | Ongoing |  | Ongoing
Note on N30: Elizna vdW: July 2023
Note on AL30: Elizna vdW: July 2023

## Review of GRAP 20
Review of GRAP 20 on Related Party Disclosures |  | Decision dates |  | Status |  | Project milestones | [9 empty] | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  | 2026/27
[13 empty] | Quarter 2 |  |  | Quarter 1 | Quarter 2 |  |  | Quarter 1 | Quarter 2
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Review the application of GRAP 20 on Related Party Disclosures |  | September 2023 |  | Project brief approved
No links with international projects.
Last history/project status:
| Prepare Review Report and other actions determined by Board |  | Dec '24 |  | Review Report approved
| Next steps: Amend GRAP 20 |  |  |  | Included in Improvements project 2025
Project actions:
#1 | Develop Project brief. |  | September 2023 |  | Project brief approved
#2 | Review and develop issues paper with the results of review and next steps |  | July 2024 |  | Consider results of review | [6 empty] | Results of Review
#3 | Prepare Review Report and other actions determined by Board |  | Dec '24 |  | Review Report approved | [8 empty] | Draft RR | Communication
#4 | Next steps: Amend GRAP 20 |  |  |  | Included in Improvements, 2026
Planned communication:
#4 | Communication of review report once published |  |  |  | Ongoing

## Review of GRAP 18
Review of GRAP 18 Segment Reporting |  | Decision dates |  | Status |  | Project milestones | [9 empty] | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  | 2026/27
[13 empty] | Quarter 2 |  |  | Quarter 1 | Quarter 2 |  |  | Quarter 1 | Quarter 2
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Review the application of GRAP 18 on Segment Reporting |  | September 2024 |  | Project brief approved
No links with international projects.
Last history/project status:
| Consider results of review |  | 2026-03-01 |  | Concluded
Project actions:
#1 | Develop Project brief. |  | September 2024 |  | Project brief approved
#2 | Review and develop issues paper with the results of review and next steps |  | 2026-03-01 |  | Results of review considered | [6 empty] | Results of Review | [6 empty] | Results of Review
#3 | Prepare Review Report and other actions determined by Board | [12 empty] | Draft RR | Communication | [6 empty] | Draft RR
Planned communication:
#4 | Communication of review report once published |  |  |  | Ongoing

## IASB Tracking Table
IASB Project |  | Status |  | Expected timing |  | Linkage with ASB Project |  | Action
https://www.ifrs.org/projects/work-plan/#all-projects
IFRS ACCOUNTING STANDARDS ISSUED
| Leases |  | IFRS 16 issued |  |  |  | IPSASB convergence project. |  | 2027 - 2029 work programme
| Revenue from Contracts with Customers |  | IFRS 15 issued |  |  |  | IPSASB convergence project. |  | Research implications for GRAP in 2027 - 2029 work programme
| Fair Value Measurement |  | IFRS 13 issued |  |  |  | IPSASB convergence project. |  | Project on Measurement
| Applying IFRS 9 with IFRS 4 |  | Issued Sept 2016 |  |  |  | N/A |  | Not applicable. See social benefits project.
| Insurance Contracts |  | IFRS 17 issued |  |  |  | Directive 5 update |  | Included in Directive 5 from 2025/26 GRAP Reporting Framework
| Management Commentary |  | Practice Statement 1 issued June 2025 |  |  |  | Monitor |  | Potential IPSASB project to monitor
| Conceptual Framework |  | Issued. |  |  |  | IPSASB convergence |  | Follow amendments to IPSASB Conceptual Framework in future work programme
| Primary financial statements (IAS 1 and IAS 7) |  | IFRS 18 issued |  |  |  | IPSASB presentation of financial statements |  | Monitor IPSASB project. Consulting concurrently.
| Disclosure initiative - Subsidiaries without public accountability |  | IFRS 19 issued |  |  |  | Monitor |  | Monitor; not considered relevant to local public sector.
| Second comprehensive review of IFRS for SMEs Accounting Standard |  | Issued |  |  |  | N/A |  | N/A
| Rate regulated activities |  | IFRS 20 issued |  |  |  | Monitor. |  | Monitor potential IPSASB project (IPSASB work programme consultation) and assess local impact for Directive 5 once effective
AMENDMENTS APPROVED
| Recoverable Amount Disclosures for Non-financial Assets (amendments to IAS 36) |  | Issued. |  |  |  | IPSASB convergence project. |  | Project on Measurement
| Sale or Contribution of Assets between an Investor and its Associate or Joint Venture (amendments to IFRS 10 and IAS 28). |  | Issued. |  |  |  | IPSASB public sector combinations project. |  | Review of IPSAS 40 GRAP 105 to 107 effective 1 April 2027
| Disclosure Initiative (amendments to IAS 7). |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Monitor IPSASB presentation project.
| Definition of a business |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Review of IPSAS 40 GRAP 105 to 107 effective 1 April 2027
| Disclosure initiative - Definition of material |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | IPSASB amendments. Consider for next Improvements
| Improvements to IFRS 8 Operating Segments following PIR |  | Issued. |  |  |  | IPSASB or IASB convergence. |  | Monitor IPSASB next work programme. Consider effect on GRAP 18. Review of GRAP 18
| Fees in 10% test for derecognition (IFRS 9) |  | Issued. |  |  |  | IASB convergence |  | Improvements, 2023 1 April 2028 submission to Minister
| PPE: Proceeds Before Intended Use |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Improvements, 2023 1 April 2028 submission to Minister
| Costs considered in assessing whether a contract is onerous |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Improvements, 2023 1 April 2028 submission to Minister
| Tax in fair value measurements (amendments to IAS 41 Agriculture) |  | Issued. |  |  |  | IPSASB or IASB convergence. |  | Monitor as part of Measurement project.
| Updating a reference to the Conceptual Framework (IFRS 3) |  | Issued. |  |  |  | IPSASB or IASB convergence. |  | References to Conceptual Framework considered. Status quo remains.
| Subsidiary as a first time adopter of IFRS |  | Issued. |  |  |  | N/A |  | Project to assess use of Directives on current work programme
| Leases incentives |  | Issued. |  |  |  | IPSASB convergence. |  | 2027 - 2029 work programme (leases)
| Accounting Policies and Accounting Estimates |  | IFRS amendments |  |  |  | IASB convergence |  | Improvements, 2023 1 April 2028 submission to Minister
| IFRS 16 and COVID-19 |  | Issued. |  |  |  | IPSASB convergence project. |  | 2027 - 2029 work programme (leases)
| IBOR reform |  | Amend IFRS |  |  |  | IPSASB convergence. |  | Improvements, 2023 1 April 2028 submission to Minister
| Supplier finance arrangements |  | Issued |  |  |  | IPSASB convergence. |  | Next improvements project. Amendments will be considered after GRAP 104 (revised) has been fully implemented.
| Lack of exchangeability (amendments to IAS 21) |  | Issued |  |  |  | IPSASB or IASB convergence. |  | Improvements, 2026
| Lease liability in a sale and leaseback transaction |  | Issued |  |  |  | IPSASB convergence. |  | 2027 - 2029 work programme (leases)
| Classification of liabilities (amendments to IAS 1). |  | Feedback statement |  |  |  | IPSASB convergence improvement |  | Improvements, 2023 1 April 2028 submission to Minister
| Amendments to Classification and measuremet of financial instruments (Amendments to IFRS 9 and IFRS 7) |  | Issued |  |  |  | IPSASB convergence improvement |  | Next improvements project. Amendments will be considered after GRAP 104 (revised) has been fully implemented.
| Improvements to IAS 7 - Cost method |  | Issued |  |  |  | IASB / IPSASB convergence |  | Improvements, 2026
| Improvements to IFRS 9 - Derecognition of lease liabilities (lessee) |  | Issued |  |  |  | IASB / IPSASB convergence |  | 2027 - 2029 work programme (leases)
| Improvements to IFRS 10 - Determination of a "de facto agent" |  | Issued |  |  |  | IASB / IPSASB convergence / GRAP 109 PIR |  | Improvements, 2026
| Improvements to IFRS 7 - Disclosure of deferred difference between fair value and transaction price (Amendments to illustrative guidance) |  | Issued |  |  |  | IASB / IPSASB convergence |  | Consider with next Improvements project. Consequential amendments to GRAP 104 may be considered following the development of the Standard of GRAP on Measurement, which includes consideration of IFRS 13.
| Improvements to IFRS 7 - Gain or loss on derecognition |  | Issued |  |  |  | IASB / IPSASB convergence |  | Next improvements project. Amendments will be considered after GRAP 104 (revised) has been fully implemented.
| Improvements to IFRS 1 - Hedge accounting by a first time adopter |  | Issued |  |  |  | N/A |  | No hedge accounting requirements in Standards of GRAP.
| Improvements to IFRS 7 - Credit Risk Disclosures (Amendments to Illustrative examples) |  | Issued |  |  |  | IASB / IPSASB convergence |  | Next improvements project. Amendments will be considered after GRAP 104 (revised) has been fully implemented.
| Improvements to IFRS 9 - Transaction price |  | Issued |  |  |  | IASB / IPSASB convergence |  | 2027 - 2029 work programme - project on revenue
| Climate-related and other uncertainties in the financial statements |  | Final illustrative exmples issued |  |  |  | 2027-2029 work programme |  | Consider for staff guidance or similar guidance on climate related disclosures in F/S (phase 2)
| Power purchase agreements (IFRS 9) |  | Issued |  |  |  | Monitor |  | To monitor potential application to GRAP 104. Amendments will be considered after GRAP 104 (revised) has been fully implemented.
| Updating the Subsidiaries without public accountability: disclosures standard |  | Issued |  |  |  | Monitor |  | Monitor; not considered relevant to local public sector.
STANDARD SETTING AND RELATED PROJECTS
| Business combinations - disclosures, goodwill and impairment |  | Decide project direction |  | Q4 2026 |  | Monitor. |  | Monitor project and consider impact on GRAP 105 to GRAP 107 once previous amendments effective.
| Equity method (IAS 28) |  | Decide project direction |  | 2026-06-01 |  | Monitor |  | Monitor and assess relevance for GRAP 36 and GRAP 37.
| Financial instruments with characteristics of equity |  | Final amendments |  | 2027 |  | Monitor |  | Monitor and assess impact on GRAP 104
| Amortised cost measurement (amendments to IFRS 9) |  | Exposure Draft |  | H2 2026 |  | Monitor |  | Consider for discussion with the GRAP 104 Reference Group
| Risk Mitigation Accounting |  | Exposure Draft Feedback |  | H2 2026 |  | Monitor |  | Consider for discussion with the GRAP 104 Reference Group although risk mitigation strategies for repricing risk may not be prevalent in the public sector
| Statement of Cash Flows and Related Matters |  | Exposure Draft |  | 2027 |  | Monitor |  | Monitor and assess impact on GRAP 2
MAINTENANCE PROJECTS
| Provisions - targeted Improvements |  | Decide project direction |  | June 2026 |  | Monitor |  | To monitor IPSASB and potential application to GRAP 19 and consider for next Improvements to GRAP as convergeance
| Translation to a Hyperinflationary Presentation Currency (IAS 21) |  | Final amendment |  | November 2025 |  | IASB or IPSASB convergence |  | To assess applicability and consider for next improvements project
| Amendments to the Fair Value Option (IAS 28) |  | Exposure Draft Feedback |  | May 2026 |  | IASB or IPSASB convergence |  | To assess applicability for GRAP 36 and consider for next improvements project
| IFRS for SMEs Accounting Standard—Consolidation Exception |  | Exposure Draft Feedback |  | Q3 2026 |  | N/A |  | N/A
RESEARCH PROJECTS
| Liabilities (Amendments to IAS 37) | [5 empty] | Project to monitor. |  | Project on hold until IASB completes conceptual framework.
| Extractive industries/intangible assets/R&D activities |  | Inactive |  |  |  | Project to monitor. |  | Monitor project and assess any impact locally (if any).
| Foreign currency translation (Research) |  | Inactive |  |  |  | Project to monitor. |  | Monitor project and assess any impact locally (if any).
| High inflation |  | Inactive |  |  |  | Project to monitor. |  | Monitor project and assess any impact locally (if any).
| Post-implementation review of IFRS 10-IFRS 12 |  | Feedback statement issued |  | Concluded |  | IASB / IPSASB convergence |  | Monitor potential future work with IASB next agenda consultation
| Post-implementation review of IFRS 9 - Impairment |  | Feedback statement |  | Concluded |  | IASB / IPSASB convergence |  | Monitor other consequential projects - amortised cost measurement and credit risk disclosures
| Post-implementation review of IFRS 15 |  | Feedback statement |  | Concluded |  | Monitor |  | Consider in revenue project
| Intangible Assets |  | Decide project direction |  | H2 2026 |  | Monitor |  | Assess how will be dealt with by IPSASB
| Post-implementation review of IFRS 16 Leases |  | Project summary and feedback statement |  | H2 2026 |  | Monitor |  | Monitor for leases project on 2027-2029 work programme
| Post-implementation review of IFRS 9 - Hedge Accounting |  | Request for information |  | Q4 2026 |  | N/A |  | N/A
APPLICATION QUESTIONS
| Classification of Cash Flows related to Variation Margin Calls on ‘Collateralised-to-Market’ Contracts (IAS 7) |  | Agenda decision |  | 2025-02-03 |  | Monitor |  | Considered with Improvements, 2026 and no amendments identified
| Determining and accounting for transaction costs (IFRS 9) |  | Agenda decision |  | 2026-02-02 |  | Monitor |  | Discussed with the GRAP 104 Reference Group. Discuss again at June 2026 meeting.
| Updates to Committee's agenda decisions for IFRS 18 |  | Agenda decision |  | 2026-05-01 |  | IASB / IPSASB convergence |  | Consider after IPSASB presentation project
| Classification of a Foreign Exchange Difference from an Intragroup Monetary Liability (or Asset) (IFRS 18) |  | Agenda decision |  | 2026-04-27 |  | Monitor |  | Unlikely to be applicable in the local public sector. IPSASB project on presentation is underway.
| Economic Benefits from Use of a Battery under an Offtake Arrangement (IFRS 16) |  | Agenda decision |  | 2026-04-27 |  | 2027-2029 work programme |  | Leases project to commence in new work programme cycle.
| Control Assessment for a Single-investor Fund (IFRS 10) |  | Decide project direction |  | 2026-06-01 |  | Monitor |  | Monitor future IFRIC discussions although unlikely implicable in the public sector
| Presentation of Taxes or Other Charges that Are Not Tax Expense or Tax Income Applying IAS 12 Income Taxes (IFRS 18) |  | Agenda decision |  | 2026-05-01 |  | N/A |  | N/A
| Reassessment of control |  | Tentative Agenda Decision Feedback |  | Q3 2026 |  | Monitor |  | Assess potential FAQ or staff guidance
GOVERNANCE PROJECTS
| Due process handbook review |  | Completed |  | 2026-04-01 |  | Assess |  | Assess impact for Due Process Handbook update.
Updated based on work plan available May 2026