## Work programme
WORK PROGRAMME FOR THE PERIOD ENDING 31 MARCH 2026
[5 empty] | 2023/24 | [11 empty] | 2026/27
| PROJECT | SECRETARIAT | CURRENT STATUS | 2022/23 |  |  |  |  | 2024/25 |  |  |  | 2025/26
|  |  |  | QUARTER 4 | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 | QUARTER 1 | QUARTER 2 | QUARTER 3 | QUARTER 4 |  | QUARTER 1
|  |  |  | (January to March 2023) | (April to June 2023) | (July to September 2023) | (October to December 2023) | (January to March 2024) | (April to June 2024) | (July to September 2024) | (October to December 2024) | (January to March 2025) | (April to June 2025) | (July to September 2025) | (October to December 2025) | (January to March 2026) |  | (April to June 2025)
MAINTAIN AND ENHANCE EXISTING STANDARDS OF GRAP AND DEVELOP NEW STANDARDS WHERE GAPS ARE IDENTIFIED
Local initiatives
| Going concern and the liquidation basis of accounting | A Botha | Submission made to Minister of Finance for proposed effective date | Submission
Maintenance of Standards
| GRAP Reporting Framework | S Nondlazi | Reporting Framework for 2026/27 to be approved |  |  | Annexure | Communication | LED | Communication | Comments | Communication |  |  | Annexure | Communication
Directive
[10 empty] | Annexure | Communication
| Improvements to the Standards of GRAP (2022) | N Imam Shah | Submission made to Minister of Finance for proposed effective date |  | Consult | GRAP | Submission Communication
| Improvements to the Standards of GRAP (2026) | S Nondlazi | Exposure Draft to be approved | [10 empty] | LED | Communication | GRAP |  | Communication
Research
Research
No research projects ongoing
Other
Other
| Work programme for 2027 to 2029 | E van der Westhuizen | Work programme 2027 - 2029 approved July 2025 | [6 empty] | LED |  |  | Final WP | Communication
| GRAP 104 reference group | N Imam Shah | Per separate work programme |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan |  | Outputs per plan
Convergence with IPSASB
| Social benefits | E van der Westhuizen | ED 214 approved / consultation in progress |  |  | ED GRAP |  |  | Issues Paper |  |  | Comments | LED | Communication |  | Comments
[6 empty] | Communication | [5 empty] | GRAP |  |  |  | GRAP
Consolidation of Directives
| Comparison with IPSAS 40 on Public Sector Combination | A Botha | Submission made to Minister of Finance for proposed effective date | ED GRAP |  |  | Comments | Submission Communication
GRAP
| Measurement | N Imam-Shah | Exposure Draft development underway |  |  | PB |  |  |  |  | IP
| - Amendments to Conceptual Framework | [13 empty] | LED | Communication
- Standard of GRAP on Measurement
| Transfer Expenses | S Nondlazi | Project brief approved September 2024
Convergence with IASB
| IFRIC 22 | N Imam-Shah | Final pronouncement approved | Communication |  | GRAP | Communication
UNDERTAKE RESEARCH TO ENSURE STANDARDS OF GRAP RESPOND TO BROADER FINANCIAL REPORTING NEEDS
| Post-implementation review of GRAP 103 on Heritage Assets | A Botha | Submission made to Minister of Finance for proposed effective date
| Post-implementation review of GRAP 109 on Accounting by Principals and Agents | E van der Westhuizen | Review Report approved | Consult | Consult | Consult |  | Comments |  | Draft RR
| - Amend GRAP 109 on Accounting by Principals and Agents | A Botha | Exposure Draft to be approved | [10 empty] | LED | Communication |  |  | GRAP
| Post-implementation review of GRAP 108 on Statutory Receivables | A Botha | Analysing responses to ED 207 |  |  | Issues Paper | LED | [5 empty] | Comments |  | Draft RR | Communication
| Review of GRAP 20 on Related Party Disclosures | S Nondlazi | Review Report approved Amendment of GRAP 20 included in Improvements project |  |  | PB |  |  | Results of Review |  | Draft RR
| Review of GRAP 18 on Segment Reporting | N Imam-Shah | Project brief approved September 2024 | [12 empty] | Results of Review
FACILITATE AND ENCOURAGE STAKEHOLDER ENGAGEMENT AND SUPPORT
| Education material for preparers of financial statements | All Standard-setters | Material recorded for YouTube |  | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan | Outputs per plan |  | Outputs per plan
Abbreviations
| Local exposure draft | LED
| Final Standard | GRAP
| Draft Directive | DD
| Final Directive | FD
| Exposure draft of an Interpretation | ED IGRAP
| Final Interpretation | IGRAP
| Draft Guideline | DG
| Final Guideline | FG
| Concurrent exposure draft (with IPSASB) | CED
| Comments on exposure draft considered by Board | Comments
| Analysis of transitional arrangements and/or effective date | Analysis
| Submission to the Minister of Finance or Accountant-General | Submission
| Comment letter to the IPSASB or IASB | Comment letter
| Project brief | PB
| Draft Research Paper | Draft RP
| Draft Review Report | Draft RR
| Issues Paper | IP
Note on AM10: Elizna van der Westhuizen: Meeting is scheduled for July 2025
Note on R56: Elizna vdW: July 2023
Note on R98: Elizna vdW: July 2023

## GRAP Reporting Framework
GRAP Reporting Framework |  | Decision dates |  | Status |  | Project milestones
[11 empty] | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
2023/24
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
To prescribe the proposed GRAP Reporting Framework for each reporting period.
| Based on results of ED 138, continue to publish ED 138, but no need to consult every year on changes to the Annexures. |  | June 2016.
Linkages with IPSASB or IASB projects
None.
Last history/project status:
| Amendments to Directive 5 and Reporting Framework for 2025/26 approved |  | 2024-09-01 |  | Final pronouncement approved
Project actions:
#1 | Approve Reporting Framework for 2026/27 |  |  |  | 2026/27 reporting framework to be approved. |  |  |  |  | LED |  | Communication | [5 empty] | Annexure 2026/27 | Communication
Approval of effective dates:
September each year in advance of commencement of affected reporting period.
Transitional provisions:
None.
Planned communication:
#2 | Articles, communication tool, recording for enhancing the application of Standards of GRAP | [7 empty] | Communication

## Improvements
Improvements to Standards of GRAP and IGRAP 22 |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
Align Standards of GRAP with latest IPSASB improvements, and IASB improvements and narrow scope amendments.
Linkages with IPSASB or IASB projects
IPSASB improvements project, and IASB improvements project and narrow scope amendments (see IASB tracking table).
Last history/project status:
| Improvements, 2023 and IGRAP 22 approved. |  | September 2023 |  | Approved
| Submission made to the Minister of Finance for Improvements, 2023 |  | December 2023 |  | Submission made to the Minister of Finance
| IFRIC 22 effective from 1 April 2025. |  | September 2023 |  | Effective 1 April 2025
Project actions:
#1 | Develop Exposure Draft of proposed Improvements (2026) |  |  |  | Exposure Draft to be approved September 2025 | [12 empty] | LED | Communication
#2 | Collate and analyse feedback and finalise amendments. Approve final Improvements |  |  |  | Approval expected March 2026 |  |  | GRAP and IGRAP | [11 empty] | GRAP |  | Communication
#3 | Make submission to the Minister of Finance for Improvements. | [7 empty] | Submission
#4
#5
Planned communication:
#6 | Opportunites to present changes and IGRAP 22 on an ongoing basis. |  | Ongoing |  | Ongoing |  |  |  | Communication

## Whole of Government Accounts (hidden)
| Whole of Government Consolidation | Decision dates |  | Status |  |  | Project milestones
2016/17
[6 empty] | Quarter 3 |  | Quarter 4 | Quarter 1
Objective:
| Position Paper to be developed by the OAG. Project arose from trilateral strategy for 2014 to 2016. |  | July 2014.
| Based on results on ED 138, decision to (1) identify current issues in preparing national and provincial consolidated financial statements, and (2) develop guidance on combined financial statements. Both projects will be undertaken in the 2017-2020 cycle. |  | June 2016.
Linkages with IPSASB or IASB projects
None
Last history:
| Position Paper to be developed by the OAG and presented to the trilateral meeting. |  | January 2015.
| ASB to undertake research in identifying issues in national and provincial consolidations, and develop guidance on combined financial statements for 2017-2020 cycle. |  | June 2016.
Current actions:
#1 | Develop project brief for identifying issues with current national and provincial consolidations. |  | August 2016. |  | Research | PB

## Citizens Reporting (hidden)
| A Citizen's Guide to Reporting | Decision dates |  | Status |  | Project milestones
[5 empty] | Quarter 3 | Quarter 4 | Quarter 1
Objective:
| To develop intergrated, plain language reporting for citizens to understand what was planned in the strategy, what resources were budgeted, how those resources were used, and what was achieved. |  | July 2014.
Linkages with IPSASB or IASB projects
None.
Last history:
| Agreed as part of trilateral strategy for 2014-2016. |  | July 2014.
| Board agreed to postpone project as part of the review of the mandate, and the possibility to expand the mandate of the ASB to reporting outside the financial statements |  | September 2014.
| Based on results on ED 138, agreed to undertake research on the need for this type of reporting. This will be commenced in the 2017-2020 cycle. |  | June 2016.
Current actions:
#1 | None at present.

## Cash Flow Statements (hidden)
| Cash Flow Statements | Decision dates |  | Status |  | Project milestones
2016/17
[5 empty] | Quarter 3 |  | Quarter 4 | Quarter 1
Objective:
| To review the presentation of specific cash flows, e.g. grants related to capital expenditure, as a result of comments received as part of the post-implementation review. |  | March 2014.
Linkages with IPSASB or IASB projects
IASB projects on (a) Disclosure Initiative - Principles of Disclosures; and (b) Proposed Narrow Scope Amendments to IAS 7.
Last history:
| Proposed review added to the work programme as a result of the post-implementation review. |  | March 2014.
| Based on feedback on ED 138, decision to undertake further work on the format of the cash flow statements. Decision to postpone any work on this area to the 2017-2020 cycle. |  | June 2016.
Current actions:
#1 | Assess possible changes during the 2017-202 cycle.

## Social benefits
Social benefits |  | Decision dates |  | Status |  |  |  | Project milestones
Project milestones
[8 empty] | 2023/24 |  |  |  | 2024/25 |  |  |  |  | 2025/26 | [5 empty] | 2026/27
[14 empty] | Quarter 2 |  |  | Quarter 1 |  | Quarter 2 |  |  |  | Quarter 1
[6 empty] | Quarter 1 |  |  | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  |  |  | Quarter 3 | Quarter 4
Objective:
| Develop a Standard of GRAP on Social Benefits. Use IPSAS 42 on Social Benefits as a starting point and modify for local environemnt. |  | September 2020 |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSAS 42 on Social Benefits
Last history/project status:
| Exposure Draft 214 approved for public consultation |  | 2025-07-01 |  | Exposure Draft approved
Project actions:
#1 | Discuss and reconfirm project brief. |  | September 2021 |  | Amended
#2 | Develop project proposal to progress project (convergence versus departure) |  | September 2021 |  | Direction agreed
#3 | Develop an Issues Paper outlining key issues on IPSAS 42 and its application locally. |  | 2022-03-01 |  | Direction agreed
#4 | Develop Exposure Draft |  | 2023-07-01 |  | Exposure Draft approved |  |  |  | LED
#5 | Comment deadline extended |  | Dec '23 |  | Comment deadline extended
#6 | Issues Paper discussed |  | 2024-07-24 |  | Issues considered
#7 | Collate and analyse feedback and finalise amendments. |  | 2025-03-25 |  | Review of responses | [10 empty] | Comments
#8 | Re-expose ED 205 as ED 214: approval of ED |  | 2025-07-25 |  | Exposure Draft approved | [12 empty] | LED |  | Communication
#9 | Collate and analyse feedback and finalise amendments. Approve final Standard of GRAP | [20 empty] | GRAP |  | Communication
#10 | Next phase: develop transitional provisions and proposed effective date
#11 | Consider consolidation of Directives
Planned communication:
#12 | Developed with Exposure Draft; activities to raise awareness through social media during public consultation process |  | Ongoing |  | Ongoing |  |  |  |  | Communication

## Review of IPSAS 40
Review of IPSAS 40 on Public Sector Combinations |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| Compare IPSAS 40 to GRAP 105 to GRAP 107 on transfers of functions and mergers. Identify what differences exist (if any), and decide if any amendments are needed to the Standards of GRAP. |  | September 2021. |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSAS 40 on Public Sector Combinations
Last history/project status:
| Approve final amendments to Standards of GRAP |  | 2023-12-01 |  | Final amendments approved
Project actions:
#1 | Develop amendments for Exposure draft. Exposure Draft approved. |  | September 2022 |  | ED approved.
#2 | Consult with stakeholders |  |  |  | Concluded |  | Communication
#3 | Collate and analyse feedback and finalise amendments. Approve final amendments to Standards of GRAP |  | 2023-12-01 |  | Approval |  |  |  | Comments and GRAP
#4 | Develop submission to the Minister on the proposed effective date |  |  |  | Submission in progress |  |  |  |  | Submission |  | Submission in progress |  |  |  |  | Submission in progress
Planned communication:
#5 | Opportunites to present approved changes identified on an ongoing basis. |  |  |  | Communication |  |  |  |  | Communication

## Measurement
Measurement |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26 |  |  |  |  | 2026/27
Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Objective:
| (i) Amend the Chapter on Measurement of Assets and Liabilities in the Conceptual Framework, based on amendments to the IPSASB Conceptual Framework. (ii) Develop a Standard of GRAP on Measurement by considering IPSAS 46 on Measurement. |  | 2023-09-01 |  | Project brief approved
Linkages with IPSASB or IASB projects
IPSASB Conceptual Framework; IPSAS 46 Measurement
Last history/project status:
| Issues paper considered and approach agreed - subsequently amended |  | July '25 |  | Approach amended
Project actions:
#1 | Approval of Project brief |  | September 2023 |  | Approved
#2 | Research and develop issues paper and agree approach to develop Exposure Drafts |  | Dec '24 |  | Approach agreed |  | Communication | [6 empty] | Issues Paper
#3 | Amended approach approved |  | July '25 |  | Approach amended
#4 | Develop Exposure Draft: Amendments to Conceptual Framework |  |  |  | Exposure Draft to be approved. | [13 empty] | LED | Communication
#5 | Analyse responses and approve amendments to CF
#6 | Develop Exposure Draft: Standard of GRAP on Measurement
#7 | Analyse responses and approve amendments to CF
Planned communication:
#8 | Awareness of discussion of issues with stakeholders, presentation on website |  | Ongoing

## Review of GRAP 109
Review of GRAP 109 on Accounting by Principals and Agents |  | Decision dates |  | Status |  | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 | [5 empty] | 2025/26 |  |  |  |  | 2026/27
[13 empty] | Quarter 2 |  |  |  | Quarter 1 | Quarter 2 |  |  |  | Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  |  | Quarter 3 | Quarter 4 |  |  |  | Quarter 3 | Quarter 4
Objective:
#1 | Undertake a post-implementation review of GRAP 109. |  | September 2021 |  | Project brief approved
#2 | Amend GRAP 109 |  | 2024-09-01 |  | Project brief approved
No links with international projects.
Last history/project status:
| Develop project brief to amend GRAP 109 |  | 2024-09-01 |  | Project brief approved
Project actions:
Phase 1: post-implementation review
#1 | Develop Project brief. |  | September 2021 |  | Project brief approved
#2 | Phase 1 of review completed. |  | May 2022 |  | Phase 1 completed
#3 | Develop consultation document. |  | November 2022 |  | ED approved |  | Consult | Consult
#4 | Collate and analyse feedback and make recommendations to the Board. |  | 2024-04-01 |  | Results of Review approved |  |  |  |  | Results of review
#5 | Communicate outcomes of review and actions agreed by the Board. |  | 2024-09-01 |  | Review Report approved | [8 empty] | Review Report
Phase 2: amend GRAP 109
#6 | Develop project brief to amend GRAP 109 |  | 2024-09-01 |  | Project brief approved
#7 | Develop responses to actions agreed by the Board: Exposure Draft to amend GRAP 109 | [17 empty] | LED | Communication
#8 | Collate and analyse feedback and finalise amendments.
#9 | Approve final amendments to Standard of GRAP
#10 | Submission to Minister of Finance
Planned communication:
#11 | Articles on Review Report |  |  |  | Published

## Review of GRAP 108
Review of GRAP 108 on Statutory Receivables |  | Decision dates |  | Status |  | Project milestones | [9 empty] | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2023/24 |  |  |  |  | 2025/26 | [6 empty] | 2026/27
[13 empty] | Quarter 2 | [9 empty] | Quarter 1 |  | Quarter 2 |  |  | Quarter 1
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  |  |  | Quarter 3 | Quarter 4
Objective:
| Undertake a post-implementation review of GRAP 108. |  | September 2021 |  | Project brief approved
No links with international projects.
Last history/project status:
| Collate and analyse feedback and approve next steps. |  | July 2025 |  | Next steps approved
Project actions:
#1 | Develop Project brief. |  | September 2021 |  | Project brief approved
#2 | Develop consultation document. |  | 2023-12-01 |  | Consultation document approved |  |  | Issues Paper | Consultation document | [8 empty] | Issues Paper | Consultation document
#3 | Collate and analyse feedback and approve next steps. |  | July 2025 |  | Next steps approved | [18 empty] | Comments
#4 | Communicate outcomes of review and actions agreed by the Board. | [24 empty] | Review Report | Communication
#5 | Develop responses to actions agreed by the Board.
Planned communication:
#6 | To communicate outcomes of review once considered by the Board. |  | Ongoing |  | Ongoing
Note on N28: Elizna vdW: July 2023
Note on AL28: Elizna vdW: July 2023

## Review of GRAP 20
Review of GRAP 20 on Related Party Disclosures |  | Decision dates |  | Status |  | Project milestones | [9 empty] | Project milestones
[6 empty] | 2023/24 |  |  |  |  | 2024/25 |  |  |  |  | 2025/26
[13 empty] | Quarter 2 |  |  | Quarter 1 | Quarter 2
[7 empty] | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  | Quarter 1 |  | Quarter 3 | Quarter 4 |  |  | Quarter 3 | Quarter 4
Objective:
| Review the application of GRAP 20 on Related Party Disclosures |  | September 2023 |  | Project brief approved
No links with international projects.
Last history/project status:
| Prepare Review Report and other actions determined by Board |  | Dec '24 |  | Review Report approved
| Next steps: Amend GRAP 20 |  |  |  | Included in Improvements project 2025
Project actions:
#1 | Develop Project brief. |  | September 2023 |  | Project brief approved
#2 | Review and develop issues paper with the results of review and next steps |  | July 2024 |  | Consider results of review | [6 empty] | Results of Review
#3 | Prepare Review Report and other actions determined by Board |  | Dec '24 |  | Review Report approved | [8 empty] | Draft RR | Communication
#4 | Next steps: Amend GRAP 20 |  |  |  | Included in Improvements project 2025
Planned communication:
#4 | Communication of review report once published |  |  |  | Ongoing

## IASB Tracking Table
IASB Project |  | Status |  | Expected timing |  | Linkage with ASB Project |  | Action
https://www.ifrs.org/projects/work-plan/#all-projects
IFRS ACCOUNTING STANDARDS ISSUED
| Leases |  | IFRS 16 issued |  |  |  | IPSASB convergence project. |  | 2027 - 2029 work programme consultation
| Revenue from Contracts with Customers |  | IFRS 15 issued |  |  |  | IPSASB convergence project. |  | Research implications for GRAP in 2027 - 2029 work programme
| Fair Value Measurement |  | IFRS 13 issued |  |  |  | IPSASB convergence project. |  | Project on Measurement
| Applying IFRS 9 with IFRS 4 |  | Issued |  |  |  | IPSASB convergence project. |  | Not applicable at present. See social benefits project.
| Insurance Contracts |  | IFRS 17 issued |  |  |  | Directive 5 update |  | Incorporate in Directive 5 from 2025/26 GRAP Reporting Framework
| Management Commentary |  | Issued |  |  |  | Monitor
| Conceptual Framework |  | Issued. |  |  |  | Next work programme |  | 2027 - 2029 work programme consultation
| IFRIC 22 Foreign Currency Transactions and Advance Consideration |  | Issued |  |  |  | IASB convergence. |  | IGRAP 22 Effective 1 April 2025
| Primary financial statements (IAS 1 and IAS 7) |  | IFRS 18 issued |  |  |  | IPSASB presentation of financial statements |  | Monitor.
| Disclosure initiative - Subsidiaries without public accountability |  | IFRS 19 issued |  |  |  | Monitor |  | Monitor; not considered relevant to local public sector.
AMENDMENTS APPROVED
| Recoverable Amount Disclosures for Non-financial Assets (amendments to IAS 36) |  | Issued. |  |  |  | IPSASB convergence project. |  | Project on Measurement
| Sale or Contribution of Assets between an Investor and its Associate or Joint Venture (amendments to IFRS 10 and IAS 28). |  | Issued. |  |  |  | IPSASB public sector combinations project. |  | Review of IPSAS 40 1 April 2026 Submission to Minister
| Disclosure Initiative (amendments to IAS 7). |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Monitor IPSASB presentation project and next work programme
| Definition of a business |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Review of IPSAS 40 1 April 2026 Submission to Minister
| Disclosure initiative - Definition of material |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | IPSASB next Improvements and next ASB work programme consultation (project on materiality).
| Improvements to IFRS 8 following PIR |  | Issued. |  |  |  | IPSASB or IASB convergence. |  | Monitor IPSASB next work programme. Consider effect on GRAP 18.
| Fees in 10% test for derecognition (IFRS 9) |  | Issued. |  |  |  | IASB convergence |  | Improvements, 2023 1 April 2026 submission to Minister
| PPE: Proceeds Before Intended Use |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Improvements, 2023 1 April 2026 submission to Minister
| Costs considered in assessing whether a contract is onerous |  | Issued. |  |  |  | IPSASB / IASB convergence. |  | Improvements, 2023 1 April 2026 submission to Minister
| Tax in fair value measurements (amendments to IAS 41) |  | Issued. |  |  |  | IPSASB or IASB convergence. |  | Monitor as part of Conceptual Framework and Measurement project.
| Updating a reference to the Conceptual Framework (IFRS 3) |  | Issued. |  |  |  | IPSASB or IASB convergence. |  | References to Conceptual Framework considered. Status quo remains.
| Subsidiary as a first time adopter of IFRS |  | Issued. |  |  |  | N/A |  | Project to assess use of Directives on current work programme
| Leases incentives |  | Issued. |  |  |  | IPSASB convergence project. |  | 2027 - 2029 work programme consultation (leases)
| Accounting Policies and Accounting Estimates |  | IFRS amendments |  |  |  | IASB convergence |  | Improvements, 2023 1 April 2026 submission to Minister
| IFRS 16 and COVID-19 |  | Issued. |  |  |  | IPSASB convergence project. |  | 2027 - 2029 work programme consultation (leases)
| IBOR reform |  | Amend IFRS |  |  |  | IPSASB convergence. |  | Improvements, 2023 1 April 2026 submission to Minister
| Supplier finance arrangements |  | Issued |  |  |  | IPSASB convergence project. |  | Next improvements project (GRAP 104)
| Lack of exchangeability (amendments to IAS 21) |  | Issued |  |  |  | IPSASB or IASB convergence. |  | Next improvements project (GRAP 4)
| Lease liability in a sale and leaseback transaction |  | Issued |  |  |  | IPSASB convergence project. |  | 2027 - 2029 work programme consultation (leases)
| Classification of liabilities (amendments to IAS 1). |  | Feedback statement |  |  |  | IPSASB convergence improvement |  | Improvements, 2023 1 April 2026 submission to Minister
| Amendments to Classification and measuremet of financial instruments (Amendments to IFRS 9 and IFRS 7) |  | Issued |  |  |  | IPSASB convergence improvement |  | Next improvements project (GRAP 104)
| Improvements to IAS 7 - Cost method |  | Issued |  |  |  | IASB / IPSASB convergence |  | Consider with next Improvements project
| Improvements to IFRS 9 - Derecognition of lease liabilities (lessee) |  | Issued |  |  |  | IASB / IPSASB convergence |  | 2027 - 2029 work programme consultation (leases)
| Improvements to IFRS 10 - Determination of a "de facto agent" |  | Issued |  |  |  | IASB / IPSASB convergence / GRAP 109 PIR |  | Consider with next Improvements project / outcome of GRAP 109 PIR
| Improvements to IFRS 7 - Disclosure of deferred difference between fair value and transaction price (Amendments to illustrative guidance) |  | Issued |  |  |  | IASB / IPSASB convergence |  | Consider with next Improvements project
| Improvements to IFRS 7 - Gain or loss on derecognition |  | Issued |  |  |  | IASB / IPSASB convergence |  | Consider with next Improvements project
| Improvements to IFRS 1 - Hedge accounting by a first time adopter |  | Issued |  |  |  | N/A |  | No hedge accounting requirements in Standards of GRAP.
| Improvements to IFRS 7 - Credit Risk Disclosures (Amendments to Illustrative examples) |  | Issued |  |  |  | IASB / IPSASB convergence |  | Consider with next Improvements project
| Improvements to IFRS 9 - Transaction price |  | Issued |  |  |  | IASB / IPSASB convergence |  | Consider with next Improvements project
STANDARD SETTING AND RELATED PROJECTS
| Management commentary |  | Final Revised Practice Statement |  | H1 2025 |  | Monitor. |  | Monitor
| Rate regulated activities |  | IFRS Accounting Standard |  | H2 2025 |  | Monitor. |  | Monitor IASB project and decide if action needed and potential IPSASB project
| Business combinations - disclosures, goodwill and impairment |  | Exposure Draft feedback |  | 2024-10-01 |  | Monitor. |  | Monitor project and consider impact on GRAP 105 to GRAP 107.
| Dynamic risk management |  | Exposure Draft |  | H1 2025 |  | Monitor |  | Monitor and assess relevance for GRAP 104
| Equity method |  | Exposure Draft |  | 2024-09-01 |  | Monitor |  | Monitor and assess relevance for GRAP 36 and GRAP 37.
| Financial instruments with characteristics of equity |  | Final amendments |  | 2026 |  | Monitor |  | Monitor and assess impact on GRAP 104
| Second comprehensive review of IFRS for SMEs Accounting Standard |  | IFRS for SMEs Accounting Standard |  | H1 2025 |  | N/A |  | N/A
MAINTENANCE PROJECTS
| Climate-related and other uncertainties in the financial statements |  | Exposure Draft feedback |  | H1 2024 |  | Monitor |  | Consider for staff guidance on climate related disclosures (phase 2)
| Power purchase agreements (IFRS 9) |  | Exposure Draft feedback |  | Áugust 2024 |  | Monitor |  | To monitor potential application to GRAP 104
| Addendum to the Exposure Draft Third edition of the IFRS for SMEs Accounting Standard |  | Exposure Draft feedback |  | 2024-09-01 |  | N/A - SMEs |  | No action
| Provisions - targeted Improvements |  | Exposure Draft |  | Q4 2024 |  | IASB or IPSASB convergence |  | To monitor potential application to GRAP 19
| Updating the Subsidiaries without public accountability: disclosures standard |  | Exposure Draft |  | H1 2025 |  | Monitor |  | Not expected to be applicable in the public sector
| Translation to a Hyperinflationary Presentation Currency (IAS 21) |  | Exposure Draft Feedback |  | H1 2025 |  | Monitor |  | To monitor potential application to GRAP 4
RESEARCH PROJECTS
| Liabilities (Amendments to IAS 37) | [5 empty] | Project to monitor. |  | Project on hold until IASB completes conceptual framework.
| Extractive industries/intangible assets/R&D activities |  | Inactive |  |  |  | Project to monitor. |  | Monitor project and assess any impact locally (if any).
| Foreign currency translation (Research) |  | Inactive |  |  |  | Project to monitor. |  | Monitor project and assess any impact locally (if any).
| High inflation |  | Inactive |  |  |  | Project to monitor. |  | Monitor project and assess any impact locally (if any).
| Post-implementation review of IFRS 10-IFRS 12 |  | Feedback statement issued |  | Concluded |  | IASB / IPSASB convergence |  | Monitor potential future work with IASB next agenda consultation
| Post-implementation review of IFRS 9 - Impairment |  | Feedback statement |  | Concluded |  | IASB / IPSASB convergence |  | Assess how will be dealt with by IPSASB
| Post-implementation review of IFRS 15 |  | Feedback statement |  | 2024-09-01 |  | Monitor |  | Assess how will be dealt with by IPSASB Monitor principal-agent issues as future IASB project
| Intangible Assets |  | Review Research |  | 2024-10-01 |  | Monitor |  | Assess how will be dealt with by IPSASB
| Post-implementation review of IFRS 16 Leases |  | Request for Information |  | H1 2025 |  | Monitor |  | Monitor for 2027 to 2029 work programme
APPLICATION QUESTIONS
| Classification of Cash Flows related to Variation Margin Calls on ‘Collateralised-to-Market’ Contracts (IAS 7) |  | Tentative Agenda Decision Feedback |  | Q4 2024 |  | Monitor |  | Assess for annual updates to FAQs / next Improvements project
| Disclosure of Revenues and Expenses for Reportable Segments (IFRS 8) |  | Agenda Decision |  | July 2024 |  | IASB / IPSASB convergence |  | Assess for annual updates to FAQs / next Improvements project
Updated based on work plan available August 2024